## URGENT Task Assignment
⚠️ PROJECT 2 - 7 PERSON TEAM - DEADLINE: TODAY MIDNIGHT ⚠️
Person | Role | Task Description | Day | Status | Priority | Notes | status':
Andrew | Project Manager | Schedule team meeting TODAY | Day 1 | Completed | CRITICAL | Get everyone aligned NOW | done
Andrew | Project Manager | Update Excel tracker daily | Ongoing | completed | High | Monitor progress hourly | in progress
Andrew | Project Manager | Track Person 2 progress (CRITICAL PATH!) | Day 1 | completed | CRITICAL | Check every 2 hours | not began
Andrew | Project Manager | Ensure Person 6 creates usp_TrackWorkFlow early | Day 2 | completed | CRITICAL | Persons 3,4,5 need this
Andrew | Project Manager | Write SQL analysis queries | Day 3 | completed | High | Query WorkflowSteps table
Andrew | Project Manager | Collect PowerPoint slides from team | Day 3 | completed | High | Each person submits
Andrew | Project Manager | Create master PowerPoint presentation | Thursday | completed | High | Assemble all slides
Andrew | Project Manager | Add voice annotation to PowerPoint | Thursday | completed | High | 12-min system lifecycle
Andrew | Project Manager | Record 12-minute SSMS demo video | Thursday | completed | High | Show complete ETL
Andrew | Project Manager | Final assembly & submit VHDX | Thursday | completed | CRITICAL | Due midnight!
Ralph | Database Architect | Restore .bak file (START NOW!) | Day 1 | Completed | CRITICAL | Everyone blocked!
Ralph | Database Architect | Create DbSecurity.UserAuthorization table | Day 1 | Completed | CRITICAL | Add all 7 members
Ralph | Database Architect | Create Process.WorkflowSteps table | Day 1 | Completed | CRITICAL | Person 6 needs this!
Ralph | Database Architect | Create DimProductCategory table | Day 1 | Completed | High | New dimension
Ralph | Database Architect | Create DimProductSubcategory table | Day 1 | Completed | High | New dimension
Ralph | Database Architect | Add 3 audit columns to ALL existing tables | Day 1 | Completed | High | UserAuthKey, DateAdded, DateOfLastUpdate
Ralph | Database Architect | Create PkSequence schema | Day 1 | Completed | High | For all sequences
Ralph | Database Architect | Create SEQUENCE objects for all tables | Day 1-2 | Completed | High | Replace IDENTITY
Ralph | Database Architect | Test all schema changes | Day 2 | Completed | High | Verify everything works
Ralph | Database Architect | Commit 01_DatabaseSchema_Setup.sql | Day 2 | Completed | High | Push to GitHub
Haroon | ETL Developer 1 | WAIT for Person 2 schema + Person 6 workflow | Day 1-2 | Completed | Blocked | Cannot start until Day 2
Haroon | ETL Developer 1 | Create [Project2].[Load_DimCustomer] | Day 2 | Completed | High | 5 dimension loaders total
Haroon | ETL Developer 1 | Create [Project2].[Load_DimGender] | Day 2 | Completed | High | Copy/modify template
Haroon | ETL Developer 1 | Create [Project2].[Load_DimMaritalStatus] | Day 2 | Completed | High | Copy/modify template
Haroon | ETL Developer 1 | Create [Project2].[Load_DimOccupation] | Day 2 | Completed | High | Copy/modify template
Haroon | ETL Developer 1 | Create [Project2].[Load_DimOrderDate] | Day 2 | Completed | High | Copy/modify template
Haroon | ETL Developer 1 | Test all 5 procedures & create PPT slides | Day 2-3 | completed | High | Verify data loads
Haroon | ETL Developer 1 | Commit 02_DimensionTables_Part1.sql | Day 3 | completed | High | Push to GitHub
Azm | ETL Developer 2 | WAIT for Person 2 schema + Person 6 workflow | Day 1-2 | completed | Blocked | Cannot start until Day 2
Azm | ETL Developer 2 | Create [Project2].[Load_DimProduct] | Day 2 | completed | High | 3 dimension loaders total
Azm | ETL Developer 2 | Create [Project2].[Load_DimProductCategory] | Day 2 | completed | High | Parent dimension
Azm | ETL Developer 2 | Create [Project2].[Load_DimProductSubcategory] | Day 2 | completed | High | Child of Category
Azm | ETL Developer 2 | Test all 3 procedures | Day 2-3 | completed | High | Verify data loads
Azm | ETL Developer 2 | Create PowerPoint slides | Day 3 | completed | Medium | Document your work
Azm | ETL Developer 2 | Commit 03_DimensionTables_Part2.sql | Day 3 | completed | High | Push to GitHub
Mohamed | ETL Developer 3 | WAIT for Person 2 schema + Person 6 workflow | Day 1-2 | Completed | Blocked | Cannot start until Day 2
Mohamed | ETL Developer 3 | Create [Project2].[Load_DimTerritory] | Day 2 | completed | High | 2 dimensions + fact
Mohamed | ETL Developer 3 | Create [Project2].[Load_DimSalesManagers] | Day 2 | completed | High | Standard dimension
Mohamed | ETL Developer 3 | Create [Project2].[Load_Data] FACT TABLE | Day 2-3 | completed | CRITICAL | Most complex - joins!
Mohamed | ETL Developer 3 | Test fact table with all dimension data | Day 3 | completed | CRITICAL | Verify joins work
Mohamed | ETL Developer 3 | Create PowerPoint slides & document joins | Day 3 | completed | Medium | Explain fact table
Mohamed | ETL Developer 3 | Commit 04_FactTable.sql | Day 3 | completed | High | Push to GitHub
Kazi | Workflow Architect | WAIT for Person 2 WorkflowSteps table | Day 1 | completed | Blocked | Need Process.WorkflowSteps
Kazi | Workflow Architect | Create Process.usp_TrackWorkFlow (URGENT!) | Day 2 AM | completed | CRITICAL | Persons 3,4,5 need NOW!
Kazi | Workflow Architect | Notify Persons 3,4,5 when ready | Day 2 AM | completed | CRITICAL | Unblock them!
Kazi | Workflow Architect | Create [Project2].[DropForeignKeysFromStarSchemaData] | Day 2 | completed | High | Drop FKs
Kazi | Workflow Architect | Create [Project2].[TruncateStarSchemaData] | Day 2 | completed | High | Clear tables
Kazi | Workflow Architect | Create [Project2].[AddForeignKeysToStarSchemaData] | Day 2 | completed | High | Recreate FKs
Kazi | Workflow Architect | Create [Project2].[LoadStarSchemaData] MASTER | Day 3 | completed | CRITICAL | Orchestrates all
Kazi | Workflow Architect | Create Process.usp_ShowWorkflowSteps | Day 3 | completed | High | Query results
Kazi | Workflow Architect | Commit 05_Workflow_MasterProcedures.sql | Day 3 | completed | High | Push to GitHub
zhenkai | JDBC Developer | Review existing JDBC library | Day 2 | completed | Medium | Understand codebase
zhenkai | JDBC Developer | Create database connection | Day 2 | completed | High | Test connection works
zhenkai | JDBC Developer | Build GUI skeleton (buttons, layout) | Day 2-3 | completed | Medium
zhenkai | JDBC Developer | WAIT for Person 6 master procedures | Day 2-3 | completed | Blocked | Need LoadStarSchemaData
zhenkai | JDBC Developer | Write code to execute [Project2].[LoadStarSchemaData] | Day 3 | completed | High | Call SP
zhenkai | JDBC Developer | Write code to execute Process.usp_ShowWorkflowSteps | Day 3 | completed | High | Get results
zhenkai | JDBC Developer | Create JTable to display workflow data | Day 3 | completed | High | The query that responsible forcreate this table not working
zhenkai | JDBC Developer | Test JDBC application thoroughly | Thursday AM | completed | CRITICAL | Must work!
zhenkai | JDBC Developer | Record 8-minute demo video | Thursday PM | completed | CRITICAL | Show app working
TASK SUMMARY BY PERSON
Person | Role | Total Tasks | Workload
Andrew Laboy | Project Manager (Andrew) | 10 | Documentation, coordination, presentations
Ralph Cange | Database Architect | 10 | Schema setup - CRITICAL PATH
Haroon Ahmed | ETL Developer 1 | 8 | 5 dimension loaders (Customer, Gender, Status, Occupation, OrderDate)
Azm Karim | ETL Developer 2 | 7 | 3 dimension loaders (Product, ProductCategory, ProductSubcategory)
Mohamed Awad | ETL Developer 3 | 7 | 2 dimension loaders (Territory, SalesManagers) + FACT TABLE
Kazi Islam | Workflow Architect | 9 | Workflow tracking + Master orchestration
zhenkai | JDBC Developer | 9 | Java application + JTable + video